AMWC WARGAME SYSTEM

Plan of Action and Milestones

Advanced Maneuver Warfare Course

Digital Transformation Roadmap -- Digitization Through AI Integration

UNCLASSIFIED // FOR OFFICIAL USE ONLY

# 1. Purpose and Scope

This Plan of Action and Milestones (POA&M) documents the development roadmap for the AMWC Wargame System. The roadmap spans five phases, from the current digitization effort through full AI-assisted adjudication and debrief generation.

## 1.1 End State

A fully integrated wargame platform where:

- All game data is captured, transmitted, and archived digitally with no paper intermediary

- Planning documents for each game are generated from structured inputs in minutes rather than hours

- A Green Cell AI provides realistic, doctrine-informed populace and information environment responses to student actions

- A Director AI adjudicates turn submissions and generates structured feedback and debrief points, enabling game execution without cadre adjudicators

## 1.2 Governing Principles

- Human authority is never displaced -- AI augments and accelerates, it does not replace commander judgment or director discretion

- Each phase must deliver standalone value -- if development stops at any phase, the tool must be more useful than before it started

- Simplicity is a feature -- the tool must be operable by cadre who are not software developers

- The platform is unclassified and must remain so throughout its development

- Student learning outcomes drive every design decision -- technical capability is a means, not an end

# 2. Phase Summary

| Ph | Phase | Focus | Est. Duration | Status |
| --- | --- | --- | --- | --- |
| 1 | Digitization | Foundation & stabilization -- multi-game portal architecture | 2-4 wks | Complete |
| 2 | Document Automation | AI-assisted game planning document generation | 6-8 wks | In Progress |
| 3 | Green Cell AI | Populace and IO response simulation | 8-10 wks | Planned |
| 4 | Director AI | Automated adjudication and debrief generation | 10-14 wks | Planned |
| 5 | Integration & Polish | End-to-end testing, training, and fielding | 4-6 wks | Planned |

NOTE -- Duration estimates assume part-time development effort (10-15 hours per week). If a dedicated developer is assigned, durations compress by approximately 50%. Phase durations do not include user acceptance testing with students, which should be scheduled at the conclusion of each phase.

# Phase 1 -- Digitization

Phase 1 encompasses the work already completed. The core platform is functional and production-ready. This phase is complete with the exception of live game validation and Firebase security review.

Objective: A stable, reliable wargame facilitation tool supporting up to six simultaneous games, accessible from the Operations Portal, with role-specific and game-specific document access.

## Phase 1 Milestones

| # | Milestone | Description / Success Criteria | Status |
| --- | --- | --- | --- |
| 1.1 | Core real-time sync | Blue, Red, and Director pages communicate reliably through Firebase. Submissions, feedback, injects, and game time sync within 2 seconds. | Complete |
| 1.2 | Turn flow integrity | Submissions archive on submit. Adjudication adds to existing records. Final turn captured regardless of end-of-game sequence. | Complete |
| 1.3 | Turn card carry-forward | Maneuver, Collections, and Fires pre-populate from previous turn. Sentinel pattern prevents Firebase node deletion. | Complete |
| 1.4 | AAR document generation | Turn history, inject log, and director notes compile into a downloadable AAR document. | Complete |
| 1.5 | Role-specific reference library | Director sees game-specific shared, director, blue, and red folders. Blue and Red see course-wide shared, role-specific, and game-specific role folders. No cross-game visibility. | Complete |
| 1.6 | Mobile and responsive UI | Top bar functional at all screen sizes. | Complete |
| 1.7 | Multi-game architecture | Game ID namespacing implemented. Up to six (or more) simultaneous games operate in isolated Firebase namespaces. Each game name maps to a folder in references/games/. | Complete |
| 1.8 | Operations Portal | Single-URL home base for all functions: game link generation, Recent Sessions, tool links, Master Director View, and reference documents organized by game. | Complete |
| 1.9 | Master Director View | Live read-only dashboard displaying all active game sessions with per-game status tiles. Auto-populates from Firebase live index. | Complete |
| 1.10 | Doc Tool -- teams | Force-locked document builder deployed for Blue and Red. Accessible from team pages and portal. | Complete |
| 1.11 | User guide and facilitation handbook v3 | Complete facilitation guide covering portal, multi-game setup, quick start guide, and updated checklists. | Complete |
| 1.12 | Live game validation | Tool runs through a complete game without technical failure. Minimum two full-game test runs with actual cadre. | In Progress |
| 1.13 | Firebase security review | Evaluate whether open read/write rules are acceptable for the operational environment. | Planned |

## Phase 1 Risks

| Risk | Likelihood | Mitigation |
| --- | --- | --- |
| Network connectivity failure in classroom | Medium | Pre-test connectivity. Identify fallback (mobile hotspot) before game day. |
| Firebase free tier limits exceeded with six simultaneous games | Low | Free tier supports 100 simultaneous connections. Six games with three tables each = 18 connections. Well within limits. |
| Browser compatibility issues on government machines | Medium | Test on the specific browsers installed on classroom machines. Chrome and Edge both support ES modules required by Firebase SDK. |

# Phase 2 -- Document Automation

Phase 2 introduces structured digital forms that enable players to rapidly enter required game information and receive formatted planning documents. The doc-tool.html and doc-tool-teams.html files represent the foundation of this capability and are functionally deployed. Remaining work focuses on expanding document types and integrating with the scenario generator.

Objective: A player can complete a structured input form covering their plan and receive a formatted, print-ready planning document within 5 minutes -- with no formatting work required.

## 2.1 Documents to be Automated

- Course of Action graphic and narrative -- scheme of maneuver text, task and purpose for each element, and COA overlay description.

- Decision Support Matrix -- key decision points mapped to triggers, criteria, and recommended actions.

- Collections Synchronization Matrix -- ISR assets tied to NAIs, PIRs, collection windows, and reporting timelines.

- Order of Battle with Task and Purpose -- complete ORBAT document with consistent structure.

- Essential Fire Support Tasks -- fire support plan formatted into a standard fire support annex.

## 2.2 Scenario Generator

The scenario generator uses the Claude API to create scenario content -- the situation, ORBAT, mission, and commander's intent -- from director-provided parameters. This accelerates scenario production so directors can develop a wider range of games without the time cost of manual scenario writing.

## Phase 2 Milestones

| # | Milestone | Description / Success Criteria | Est. Effort | Status |
| --- | --- | --- | --- | --- |
| 2.1 | Document builder interface (Blue/Red) | Structured input forms deployed as doc-tool-teams.html. Force-locked, generates DOCX. Integrated into team pages and portal. | Complete | Complete |
| 2.2 | Document builder interface (Director) | Full unlocked doc-tool.html deployed. Accessible from director page and portal. | Complete | Complete |
| 2.3 | COA and DSM templates | Players input scheme of maneuver and decision points. Tool populates formatted templates. Output as DOCX. | ~8 hrs | In Progress |
| 2.4 | Collections sync matrix template | Players input ISR assets, NAIs, PIRs, and collection windows. Tool assembles a formatted sync matrix. | ~6 hrs | In Progress |
| 2.5 | ORBAT with task and purpose template | Players input each element with task and purpose. Tool assembles a formatted ORBAT document. | ~4 hrs | In Progress |
| 2.6 | Essential fire support tasks template | Players input EFSTs, priority targets, no-fire areas, and FSCMs. Tool formats them into a standard fire support annex. | ~4 hrs | In Progress |
| 2.SG1 | Scenario parameter input form | Director input form: AO, date/time, friendly force type, adversary type, weather, and primary learning objective. | ~6 hrs | In Progress |
| 2.SG2 | Blue Force document generator | AI generates Blue Force situation brief matching the established course format. Output as DOCX. | ~10 hrs | In Progress |
| 2.SG3 | PLA adversary force generator | AI generates Red Force situation brief using PLA order of battle, equipment, and operational doctrine. | ~10 hrs | In Progress |
| 2.SG4 | Russian adversary force generator | AI generates Red Force situation brief using Russian BTG structure, equipment, and operational doctrine. | ~8 hrs | In Progress |
| 2.SG5 | Scenario package validation | Generated scenarios reviewed by SME against doctrinal accuracy. Correction workflow established. | ~8 hrs | Planned |
| 2.10 | Phase 2 live game validation | Complete game run using AI-generated documents. Cadre assess document quality against manually produced equivalents. | ~4 hrs | Planned |

# Phase 3 -- Green Cell AI

Phase 3 introduces a Green Cell AI that monitors Blue and Red submissions each turn, evaluates IO-relevant actions, and delivers structured populace response feedback through the existing inject system, without requiring human Green Cell staffing.

Objective: A Green Cell AI that operates each turn without cadre staffing and delivers responses that cadre rate as doctrinally plausible and scenario-appropriate in at least 80% of cases.

## Phase 3 Milestones

| # | Milestone | Description / Success Criteria | Est. Effort | Status |
| --- | --- | --- | --- | --- |
| 3.1 | Green Cell context architecture | Design the AI's persistent context: scenario parameters, populace baseline, running sentiment state, and per-turn action log. | ~8 hrs | Planned |
| 3.2 | IO action recognition | AI correctly identifies IO-relevant actions from turn card submissions. | ~10 hrs | Planned |
| 3.3 | Populace response narrative generator | AI generates a 3-5 sentence populace response narrative per force per turn. | ~12 hrs | Planned |
| 3.4 | Sentiment tracking model | Simple 1-10 sentiment score per population group, updated each turn. Director sees trend line across turns. | ~8 hrs | Planned |
| 3.5 | Director review interface | Green Cell outputs appear on a new Director Green Cell tab before being pushed as injects. Director approves, edits, or discards each response. | ~10 hrs | Planned |
| 3.6 | Integration with inject system | Approved Green Cell responses pushed through the existing inject system as Green Cell inject type. | ~4 hrs | Planned |
| 3.7 | Doctrinal grounding | Provide AI with relevant doctrinal references as system context. Validate outputs with SME review. | ~8 hrs | Planned |
| 3.8 | Phase 3 live game validation | Complete game run with Green Cell AI active. Cadre and student assessment of realism and training value. | ~6 hrs | Planned |

# Phase 4 -- Director AI

Phase 4 introduces a Director AI capable of adjudicating turn submissions, generating structured feedback for both forces, and producing debrief points grounded in the students' actual decisions. Fully realized, this phase enables the platform to run games without a human adjudicator.

Objective: An AI director that adjudicates turn submissions using doctrine, scenario parameters, and game state, delivers feedback to teams within 60 seconds of submission, and generates a structured debrief package grounded in specific student decisions.

## Phase 4 Milestones

| # | Milestone | Description / Success Criteria | Est. Effort | Status |
| --- | --- | --- | --- | --- |
| 4.1 | Adjudication engine design | Define the adjudication framework: inputs, outputs, doctrine sources, and evaluation criteria for each phase. | ~12 hrs | Planned |
| 4.2 | Doctrine knowledge base | Compile and structure relevant doctrinal references as AI context. FM 3-0, FM 3-90, MCDP 1-3, MCWP 3-11.3, Kriegsspiel rules. | ~16 hrs | Planned |
| 4.3 | Collections adjudication | AI generates ISR results: PIR answers, partial answers, and open items. | ~10 hrs | Planned |
| 4.4 | Maneuver adjudication | AI generates movement outcomes and contact results. | ~14 hrs | Planned |
| 4.5 | Fires adjudication | AI adjudicates fire missions: execution, effects, BDA, and asset status update. | ~10 hrs | Planned |
| 4.6 | Director review interface | AI-generated adjudication appears in director panel fields for review before push. | ~8 hrs | Planned |
| 4.7 | Debrief package generator | AI generates structured debrief document from complete turn history at end of game. | ~12 hrs | Planned |
| 4.8 | Autonomous game mode | Full game execution without human adjudicator. AI handles all adjudication and feedback. | ~16 hrs | Planned |
| 4.9 | Exportable scenario package | Complete game package exportable for use by any unit without AMWC infrastructure. | ~8 hrs | Planned |
| 4.10 | Phase 4 live game validation | Two full-game runs: one with human director review of AI outputs, one in autonomous mode. | ~8 hrs | Planned |

# Phase 5 -- Integration and Polish

Phase 5 is the integration and hardening phase. It does not introduce new AI capabilities but ensures all capabilities work reliably together, adds student records management, and prepares the platform for formal fielding.

Objective: A production-quality platform that can be handed to any AMWC class without technical support, with a clear sustainment and update process.

## Phase 5 Milestones

| # | Milestone | Description / Success Criteria | Est. Effort | Status |
| --- | --- | --- | --- | --- |
| 5.1 | End-to-end integration testing | Complete 3-game run exercising all capabilities. All defects documented and resolved. | ~16 hrs | Planned |
| 5.2 | Student records management | Track student performance across multiple games. Flag recurring patterns for cadre attention. | ~12 hrs | Planned |
| 5.3 | Cross-game trend analysis | AI identifies patterns across a student's game history. | ~8 hrs | Planned |
| 5.4 | Performance dashboard for cadre | Cadre view of all student performance across the course. | ~8 hrs | Planned |
| 5.5 | Scenario library and version control | Library of validated scenarios organized by terrain, scenario type, and learning objective. | ~8 hrs | Planned |
| 5.6 | Facilitated vs. autonomous mode selector | Cadre select the operating mode at game start. | ~6 hrs | Planned |
| 5.7 | Sustainment documentation | Technical documentation for maintaining Firebase, updating the Claude API integration, managing GitHub Pages deployment, and troubleshooting. | ~8 hrs | Planned |
| 5.8 | Training package for new cadre | Onboarding package for new AMWC cadre covering tool operation, scenario building, AI output review, and debrief facilitation. | ~6 hrs | Planned |
| 5.9 | Formal fielding | Tool officially adopted as part of AMWC curriculum. Scenario library populated with at least 6 validated scenarios. | Admin | Planned |

# 6. Dependencies and Sequencing

The phases are broadly sequential with some overlap permitted.

- Phase 2 (Document Automation) requires Phase 1 completion -- the scenario builder writes to the reference library.

- Phase 3 (Green Cell AI) requires Phase 2 completion -- the Green Cell AI uses scenario parameters generated by the Phase 2 scenario builder.

- Phase 4 (Director AI) requires Phase 3 completion -- the Director AI and Green Cell AI share context and must be coordinated.

- Phase 5 (Integration) requires Phase 4 completion.

Permitted parallel work:

- Phase 1.12 and 1.13 (live validation and security review) can run concurrently with Phase 2 design work.

- Phase 5 documentation work can begin as early as Phase 3 completion.

# 7. Technology Stack

The platform uses a deliberately minimal, free-tier technology stack to avoid cost, maintenance burden, and infrastructure complexity.

| Layer | Technology | Notes |
| --- | --- | --- |
| Frontend | HTML / CSS / JavaScript (four files) | Hosted on GitHub Pages. No server required. Single-page files for Portal, Game (index), and Dashboard. |
| Real-time database | Firebase Realtime Database (free Spark tier) | Handles all game state synchronization across all simultaneous games. |
| AI | Claude API (Anthropic -- claude-sonnet-4-20250514) | Used for document generation (Phase 2), Green Cell responses (Phase 3), and adjudication (Phase 4). |
| Document generation | docx-js library | DOCX output. Run client-side. Deployed in doc-tool.html and doc-tool-teams.html. |
| Version control and hosting | GitHub | All code, documents, and reference files in a single public repository. |

API KEY SECURITY -- The Claude API key must not be embedded directly in the client-side HTML once AI features are added in Phase 2. A lightweight proxy -- either a Cloudflare Worker or GitHub Actions workflow -- should handle API calls server-side to protect the key. Both Cloudflare Workers and GitHub Actions are free at the usage levels expected.

# 8. Success Metrics

| Phase | Success Criteria |
| --- | --- |
| Phase 1 | Zero technical failures in two complete live game runs. All six simultaneous games operate without cross-contamination. All cadre can operate the tool after a 30-minute orientation. |
| Phase 2 | A complete game planning document package generated in under 15 minutes from a blank form. Cadre assess AI-generated documents as acceptable for game use after review in at least 80% of cases. |
| Phase 3 | Green Cell AI generates responses that cadre rate as doctrinally plausible and scenario-appropriate in at least 80% of cases. Students engage with IO dimension more explicitly than in games without Green Cell. |
| Phase 4 | AI adjudication rated as credible by at least 80% of student reviewers. Autonomous mode game generates debrief package that cadre assess as usable with minor modification. At least one unit uses the exportable package independently post-graduation. |
| Phase 5 | New cadre member operates the tool successfully after onboarding with documentation only. Scenario library contains 6 validated scenarios. Platform operates for a full course iteration without cadre-reported technical failures. |

AMWC Wargame System -- Plan of Action and Milestones

UNCLASSIFIED // FOR OFFICIAL USE ONLY